## Plan
CADDI RESOURCE PLAN
| Feature | Design | Dev | Test | Total | Description
1 | Setup Infra | 1 | 3 | 1 | 5 | Dev, Staging, Production
2 | Setup code base | 1 | 2 | 0 | 3
3 | User service | 1.5 | 5 | 2.5 | 9 | 5 flows: authen, signup, login, auth, logout
4 | Chat api service | 2 | 8 | 4 | 14 | create topic, get topic, delete topic, upload image, subscrible topic, unsubscrible topic.
5 | Websocket chat service | 2 | 8 | 4 | 14 | connect, disconnect, send message, load message.
6 | Integration test | 0 | 0 | 3 | 3
| Total | 7.5 | 26 | 14.5 | 48
Unit: Man-day
QC: | 14.5
Dev: | 33.5