## Plan
CADDI RESOURCE PLAN | [6 empty] | Unit: Man-day
| Feature | Design | Dev | Test | Total | Description
1 | Setup Infra | 3 | 5 | 1 | 9 | Dev, staging, production
2 | Managed Infra | 0 | 5 | 1 | 6 | Scaleup, scale down.
3 | Setup code base | 1 | 2 | 0 | 3
4 | User service | 1.5 | 5 | 2.5 | 9 | 5 flows: authen, signup, login, auth, logout
5 | Chat api service | 2 | 8 | 4 | 14 | create topic, get topic, delete topic, upload image, subscrible topic, unsubscrible topic.
6 | Websocket chat service | 2 | 8 | 4 | 14 | connect, disconnect, send message, load message.
7 | Integration test | 0 | 0 | 3 | 3
| Total | 9.5 | 33 | 15.5 | 58
QC: | 15.5
Dev: | 42.5